UNIT–2 AGILE MINI-PROJECT

Student Record and Academic Management Platform

Detailed Agile Project Planning and Scrum Documentation

# Table of Contents

1. Product Discovery and Business Understanding

2. Agile Product Vision

3. Scrum Team Structure

4. Scrum Roles and Responsibilities

5. Epic Documentation

6. User Story Repository

7. Acceptance Criteria Document

8. Prioritized Product Backlog

9. Story Point Estimation

10. Sprint Planning

11. Sprint Backlog

12. Scrum Board

13. Burndown Chart

14. Scrum Ceremonies

15. Sprint Review Report

16. Sprint Retrospective Report

17. Agile Framework Comparison

18. Project Timeline and Release Roadmap

19. Complete Agile Documentation Checklist

20. Conclusion

1. Product Discovery and Business Understanding

The Agile work begins by reviewing the product-discovery information developed in Unit 1. This step ensures that the Scrum team understands why the system is being developed, who will use it, what problems it must solve, and what the first useful release should contain.

## 1.1 Product Vision

The proposed system is a secure, user-friendly Student Record and Academic Management Platform that brings student information, attendance, academic performance, course registration, notifications, and reporting into one organized application.

## 1.2 Product Mission

The mission is to reduce manual academic record work, improve accuracy, make information easier to access, and provide students, faculty, and administrators with timely and reliable academic information.

## 1.3 Main Stakeholders

| Stakeholder | Interest / Responsibility |
| --- | --- |
| Students | View profile, courses, attendance, marks, results and notifications. |
| Faculty | Manage courses, record attendance, enter marks and generate academic information. |
| Academic Administrators | Maintain student records, courses, reports and system-level academic data. |
| System Administrator | Manage accounts, access rights, security and technical configuration. |
| Management | Use reports and summaries for academic monitoring and decision-making. |

## 1.4 Business Requirements

Centralize student and academic information in one platform.

Reduce duplicate and paper-based record maintenance.

Make attendance and marks easier to maintain.

Provide quick access to academic reports.

Protect student information through authentication and role-based access.

Allow the platform to grow as the number of users and records increases.

## 1.5 Functional Requirements

Student registration and profile management.

Course creation, update and student assignment.

Attendance recording, viewing and reporting.

Marks entry, updating, grade calculation and result sheets.

Login, logout, password reset and role-based access.

Attendance, examination and result notifications.

Student, attendance, performance and course reports.

## 1.6 Non-Functional Requirements

Security: only authorized users should access protected information.

Usability: screens and workflows should be simple for students and staff.

Reliability: academic records should be stored consistently and be available when needed.

Performance: common actions such as login, search and viewing records should respond quickly.

Scalability: the design should support more students, courses and academic records over time.

Maintainability: modules should be organized so future changes can be made easily.

## 1.7 User Personas

| Persona | Needs | Typical Actions |
| --- | --- | --- |
| Student | Easy access to personal academic information | Login, view courses, attendance, marks and notifications. |
| Faculty Member | Efficient academic record entry | Select course, record attendance, enter marks, view reports. |
| Academic Administrator | Central control of academic records | Add/search/update students, manage courses and reports. |
| System Administrator | Secure user and system management | Manage accounts, roles, passwords and access. |

## 1.8 Minimum Viable Product (MVP)

The MVP should provide the smallest useful release that demonstrates the core academic workflow. It should include authentication, basic student management, course management, attendance recording, and basic academic reporting. Advanced analytics and additional notification features can be added in later releases.

## 1.9 Product Roadmap

| Release | Main Scope |
| --- | --- |
| Release 1 – Foundation | Project setup, registration, login and basic interface. |
| Release 2 – Student Management | Add, search, update and delete student records. |
| Release 3 – Academic Management | Course management, course assignment and attendance. |
| Release 4 – Performance | Marks, grades, result sheets and performance reporting. |
| Release 5 – Enhancement | Notifications, dashboards, advanced reports and analytics. |

# 2. Agile Product Vision

The Agile product vision converts the business problem into a clear direction for iterative development. Instead of trying to build every feature at once, the team delivers useful functionality in small increments and improves the product using feedback.

## 2.1 Overall Objective

Develop a secure and easy-to-use web-based platform that manages student records and academic activities such as courses, attendance, marks and reports.

## 2.2 Primary Users

Students

Faculty members

Academic administrators

System administrators

## 2.3 Expected Business Benefits

Less manual data entry and paperwork.

Better accuracy and consistency of academic records.

Faster access to student and course information.

Improved transparency of attendance and academic performance.

Better security through controlled user access.

Improved decision-making through organized reports.

## 2.4 Measurable Success Criteria

| Area | Target / Indicator |
| --- | --- |
| Authentication | Registered users can successfully log in and invalid credentials are rejected. |
| Student records | Authorized staff can add, search, update and delete records. |
| Attendance | Faculty can record attendance and retrieve attendance information. |
| Academic data | Marks can be entered/updated and grades/results can be generated. |
| Reporting | Required academic reports can be generated from stored records. |
| Usability | Common tasks can be completed through clear and understandable screens. |
| Security | Role-based access prevents unauthorized actions. |

## 2.5 Constraints and Assumptions

The project is developed incrementally within academic project constraints.

Requirements may be refined after stakeholder feedback.

The initial release focuses on core academic workflows rather than advanced analytics.

Users require valid credentials for protected functions.

The team must balance functionality, testing, documentation and time.

## 2.6 Expected Software Capabilities

Manage student profiles and records.

Manage courses and student-course assignments.

Record and view attendance.

Maintain marks and academic performance.

Authenticate users and control access by role.

Send relevant academic notifications.

Generate academic and administrative reports.

# 3. Scrum Team Structure

The project uses a Scrum team in which responsibilities are clearly divided but team members collaborate closely. The Product Owner focuses on value and priorities, the Scrum Master supports the Scrum process, and the Development Team converts requirements into a working increment.

| Role | Main Focus | Key Responsibilities |
| --- | --- | --- |
| Product Owner | Product value and requirements | Manage product vision, prioritize backlog, clarify requirements, represent stakeholder interests and accept completed work. |
| Scrum Master | Scrum process | Facilitate ceremonies, remove impediments, support Agile practices and improve team collaboration. |
| Development Team | Working product | Design, code, test, integrate, document and demonstrate the software increment. |

## 3.1 Suggested Team Structure

1 Product Owner – represents academic and stakeholder needs.

1 Scrum Master – coordinates Scrum activities and removes process obstacles.

Developers – implement frontend, backend and database functions.

Tester/QA responsibility – verifies acceptance criteria and detects defects.

Documentation responsibility – maintains Agile and technical documentation.

# 4. Scrum Roles and Responsibilities

## 4.1 Product Owner

Defines and communicates the product vision.

Collects and clarifies stakeholder requirements.

Creates and prioritizes the Product Backlog.

Ensures high-value features are developed first.

Clarifies acceptance criteria when questions arise.

Reviews completed work and decides whether it meets the expected outcome.

## 4.2 Scrum Master

Facilitates Sprint Planning, Daily Scrum, Sprint Review and Retrospective.

Helps the team follow Scrum principles.

Identifies and removes impediments.

Encourages communication and collaboration.

Protects the team from unnecessary disruption.

Supports continuous improvement.

## 4.3 Development Team

Breaks stories into implementable tasks.

Designs the solution and writes code.

Creates and maintains database and interface components.

Tests features against acceptance criteria.

Fixes defects and integrates completed work.

Demonstrates the working increment during Sprint Review.

Maintains necessary technical documentation.

# 5. Epic Documentation

An Epic is a large feature or business capability that is too broad to complete as one small user story. Each epic is divided into smaller stories that can be estimated, developed and tested.

## Epic 1 – Student Management

Goal: Maintain student registration and academic profile information.

Main capabilities: Registration, profile view/update, search, deletion.

## Epic 2 – Course Management

Goal: Manage courses and student-course relationships.

Main capabilities: Add/update course, assign students, view course details.

## Epic 3 – Attendance Management

Goal: Maintain accurate attendance records.

Main capabilities: Record attendance, view attendance, generate reports.

## Epic 4 – Marks and Academic Performance

Goal: Maintain marks and calculate academic outcomes.

Main capabilities: Enter/update marks, calculate grades, generate result sheets.

## Epic 5 – Authentication and Security

Goal: Protect the platform and control access.

Main capabilities: Login, logout, password reset, role-based access.

## Epic 6 – Notifications

Goal: Keep users informed about important academic events.

Main capabilities: Attendance, examination and result notifications.

## Epic 7 – Reporting

Goal: Provide useful academic and administrative reports.

Main capabilities: Student, attendance, performance and course reports.

# 6. User Story Repository

User stories describe requirements from the user's point of view. The standard format is: “As a [user], I want [feature], so that [benefit].”

| ID | Story | User Story Summary | Priority | Points |
| --- | --- | --- | --- | --- |
| US01 | Student Login | As a registered user, I want to log in securely so that I can access my academic information. | High | 5 |
| US02 | Student Registration | As an administrator, I want to register a student so that the student has a system record. | High | 5 |
| US03 | Search Student | As an administrator, I want to search for a student so that I can quickly find the required record. | High | 3 |
| US04 | Update Student | As an administrator, I want to update student details so that records remain current. | High | 3 |
| US05 | Delete Student | As an authorized administrator, I want to delete a student record so that obsolete records can be removed. | Medium | 3 |
| US06 | Add Course | As an administrator, I want to add a course so that students can be associated with available courses. | Medium | 3 |
| US07 | Assign Course | As an administrator, I want to assign students to courses so that academic enrollment is maintained. | Medium | 5 |
| US08 | Record Attendance | As a faculty member, I want to record attendance for a course and date so that attendance records remain accurate. | High | 5 |
| US09 | Attendance Report | As a faculty member, I want to generate an attendance report so that I can monitor student attendance. | Medium | 5 |
| US10 | Enter Marks | As a faculty member, I want to enter student marks so that academic performance can be maintained. | High | 5 |
| US11 | Calculate Grades | As the system, I want to calculate grades from marks so that results are consistent. | Medium | 5 |
| US12 | Password Reset | As a user, I want to reset my password so that I can regain access if I forget it. | Medium | 3 |
| US13 | Notifications | As a student, I want to receive important academic notifications so that I do not miss key updates. | Medium | 5 |
| US14 | Academic Dashboard | As a student or administrator, I want a summary dashboard so that important academic information is visible quickly. | Low | 8 |

# 7. Acceptance Criteria Document

Acceptance criteria are clear and measurable conditions used to decide whether a user story is complete. A story should not be treated as finished merely because coding has stopped; it should satisfy its agreed criteria and be tested.

## US01 – Student Login

Login page loads correctly.

Registered users can enter valid credentials.

Invalid credentials display an appropriate error.

Successful login redirects the user to the dashboard.

Session/access behavior works as expected.

## US02 – Student Registration

Authorized administrator can open registration.

Required fields are validated.

A valid record is saved.

Duplicate/invalid data is rejected appropriately.

The new student can be found after registration.

## US03 – Search Student

Search screen is accessible to authorized users.

Search can use appropriate student information.

Matching records are displayed.

No-match searches show a clear result.

Unauthorized users cannot access protected records.

## US08 – Record Attendance

Faculty can select a course and date.

Students associated with the course are displayed.

Attendance can be marked.

The record can be saved successfully.

Saved attendance can be viewed or used in reports.

## US10 – Enter Marks

Faculty can select the relevant course/student.

Marks are accepted within the defined range.

Invalid values are rejected.

Valid marks are saved.

Updated marks appear correctly when viewed again.

## US13 – Notifications

Relevant academic event creates a notification.

Notification reaches the intended user.

Notification contains understandable information.

Users can view notification status/content.

# 8. Prioritized Product Backlog

The Product Backlog is a single ordered list of work needed to improve the product. Prioritization considers business value, user importance, technical dependencies and implementation complexity.

| Rank | ID | Backlog Item | Priority | Points | Planned Sprint |
| --- | --- | --- | --- | --- | --- |
| 1 | US01 | Student Login | High | 5 | Sprint 1 |
| 2 | US02 | Student Registration | High | 5 | Sprint 1 |
| 3 | US03 | Search Student | High | 3 | Sprint 2 |
| 4 | US04 | Update Student | High | 3 | Sprint 2 |
| 5 | US08 | Record Attendance | High | 5 | Sprint 3 |
| 6 | US10 | Enter Marks | High | 5 | Sprint 4 |
| 7 | US06 | Add Course | Medium | 3 | Sprint 3 |
| 8 | US07 | Assign Course | Medium | 5 | Sprint 3 |
| 9 | US09 | Attendance Report | Medium | 5 | Sprint 3 |
| 10 | US12 | Password Reset | Medium | 3 | Sprint 1/2 |
| 11 | US11 | Calculate Grades | Medium | 5 | Sprint 4 |
| 12 | US13 | Notifications | Medium | 5 | Sprint 5 |
| 13 | US05 | Delete Student | Medium | 3 | Sprint 2 |
| 14 | US14 | Academic Dashboard | Low | 8 | Sprint 5 |

## 8.1 Prioritization Logic

High priority items are essential to the first usable academic workflow.

Medium priority items improve completeness and operational usefulness.

Low priority items provide enhancement value after core functions are stable.

Dependencies are considered before assigning work to a Sprint.

Priorities can be revised when stakeholder feedback changes the product need.

# 9. Story Point Estimation

Story points estimate relative effort and complexity rather than exact hours. The project follows the requested scale: 1, 2, 3, 5, 8 and 13.

| Points | Meaning | Example |
| --- | --- | --- |
| 1 | Very Easy | Small text/UI adjustment or simple configuration. |
| 2 | Easy | Small change with limited logic. |
| 3 | Moderate | Straightforward feature requiring development and testing. |
| 5 | Difficult | Feature involving multiple components or validation. |
| 8 | Very Difficult | Large feature with significant coordination or uncertainty. |
| 13 | Highly Complex | Very large/uncertain work; should normally be split into smaller stories. |

## 9.1 Planning Poker

Each team member independently selects a point value.

All estimates are revealed together.

Large differences are discussed, especially the reasons behind high or low estimates.

The team estimates again after discussion.

The agreed estimate is recorded in the backlog.

## 9.2 Example Estimation

| Story | Factors Considered | Estimate |
| --- | --- | --- |
| Student Login | UI, authentication logic, validation, session handling and testing | 5 |
| Search Student | Search input, database query, results and testing | 3 |
| Record Attendance | Course/date selection, student list, saving and reporting integration | 5 |
| Academic Dashboard | Multiple data sources, summaries, UI and higher uncertainty | 8 |

# 10. Sprint Planning

Sprint Planning converts prioritized Product Backlog items into a Sprint Goal and a Sprint Backlog. The team selects work that it believes can be completed within the Sprint while maintaining the Definition of Done.

## 10.1 Sprint 1 – Authentication and Project Setup

Sprint Goal: Establish the project foundation and provide secure basic access.

Initialize repository and project structure.

Set up basic database structure.

Implement student/user registration.

Implement login and logout.

Create basic UI/navigation.

Write and execute initial tests.

## 10.2 Sprint 2 – Student Management

Sprint Goal: Provide reliable management of student records.

Add student record.

Search student records.

Update student information.

Delete student records where authorized.

Validate inputs and access rights.

Test student-management workflows.

## 10.3 Sprint 3 – Course and Attendance

Sprint Goal: Enable core academic activity management.

Add/update courses.

Assign students to courses.

Select course and date.

Record attendance.

View attendance.

Generate attendance reports.

## 10.4 Sprint 4 – Marks and Performance

Enter marks.

Update marks.

Calculate grades.

Generate result sheets.

Test academic calculations and permissions.

## 10.5 Sprint 5 – Notifications and Reporting

Attendance notifications.

Examination/result notifications.

Student and performance reports.

Academic dashboard enhancements.

Final integration and usability improvements.

# 11. Sprint Backlog

| Sprint | Selected Work | Approx. Points | Sprint Goal |
| --- | --- | --- | --- |
| Sprint 1 | US01, US02 + setup tasks | 10+ setup | Secure access and project foundation |
| Sprint 2 | US03, US04, US05 | 9 | Complete core student record management |
| Sprint 3 | US06, US07, US08, US09 | 18 | Course and attendance workflow |
| Sprint 4 | US10, US11 | 10 | Marks and academic performance |
| Sprint 5 | US12, US13, US14 + improvements | 16 | Notifications, dashboard and refinement |

## 11.1 Definition of Done

Requirements and acceptance criteria are understood.

Code is implemented and integrated.

Relevant tests are completed.

Known critical defects are fixed.

Feature behaves as expected in the target environment.

Documentation is updated where required.

Product Owner can review a working increment.

# 12. Scrum Board

The Scrum Board makes work visible. A simple workflow for this project is Backlog → To Do → In Progress → Testing → Completed.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Academic Dashboard | Add Course | Student Login | — | Project setup |
| Notifications | Assign Course | Student Registration | — | Basic navigation |
| Password Reset | Search Student | — | — | — |
| Result Sheet | Attendance Report | — | — | — |

## 12.1 Meaning of Each Column

Backlog: ideas or future work not yet selected.

To Do: selected work waiting to begin.

In Progress: work currently being developed.

Testing: development is finished and the feature is being verified.

Completed: acceptance criteria and Definition of Done are satisfied.

# 13. Burndown Chart

A burndown chart shows remaining work during a Sprint. The example below is an illustrative Sprint 3 tracking table; actual values should be updated from the team's real task board.

| Day | Remaining Story Points |
| --- | --- |
| Day 1 | 18 |
| Day 2 | 16 |
| Day 3 | 14 |
| Day 4 | 12 |
| Day 5 | 11 |
| Day 6 | 8 |
| Day 7 | 6 |
| Day 8 | 4 |
| Day 9 | 2 |
| Day 10 | 0 |

Interpretation: The ideal direction is downward because completed work reduces remaining effort. If the line stops decreasing, the Scrum team should discuss blockers during the Daily Scrum and take corrective action.

# 14. Scrum Ceremonies

## 14.1 Sprint Planning

Review product priorities.

Select stories for the Sprint.

Estimate and confirm capacity.

Define a clear Sprint Goal.

Break selected stories into tasks.

## 14.2 Daily Scrum

A short daily synchronization meeting where the team discusses progress, upcoming work and challenges. Typical questions are what was completed, what will be worked on next, and whether anything is blocking progress.

## 14.3 Sprint Review

Demonstrate the working increment.

Collect stakeholder feedback.

Check whether the Sprint Goal was achieved.

Discuss backlog changes suggested by feedback.

## 14.4 Sprint Retrospective

Discuss what went well.

Identify problems or delays.

Find the root cause where useful.

Agree on practical improvements for the next Sprint.

# 15. Sprint Review Report

A Sprint Review focuses on the product increment rather than only on the amount of work completed. The team demonstrates working features to stakeholders and uses their feedback to improve the Product Backlog.

| Review Area | Expected Demonstration | Feedback / Action |
| --- | --- | --- |
| Authentication | Registration, login and logout | Confirm ease of use and access behavior. |
| Student Management | Add, search, update and delete | Check required fields and search usability. |
| Attendance | Record and view attendance | Confirm course/date workflow and report usefulness. |
| Course Management | Add course and assign students | Confirm enrollment workflow. |
| Performance | Marks and result features | Confirm grade/result presentation. |

## 15.1 Review Outcome

Accepted stories remain part of the completed increment. Stories that need changes are returned to the Product Backlog with updated acceptance criteria or priority. New stakeholder needs are also added to the backlog rather than being inserted informally into an active Sprint.

# 16. Sprint Retrospective Report

| Area | Observation | Improvement Action |
| --- | --- | --- |
| What went well | Core requirements were divided into manageable stories. | Continue story-level planning. |
| What went well | The Scrum Board made progress visible. | Keep board updated daily. |
| Challenge | Some stories may involve more effort than first estimated. | Discuss uncertainty during Planning Poker. |
| Challenge | Integration can create late defects. | Integrate and test continuously. |
| Improvement | Acceptance criteria can prevent ambiguity. | Write measurable criteria before development. |
| Improvement | Communication reduces blockers. | Raise blockers early in Daily Scrum. |

## 16.1 Retrospective Method

Start with facts from the Sprint.

Identify positive practices to continue.

Identify problems without blaming individuals.

Choose a small number of high-impact improvements.

Assign ownership where appropriate and review progress in the next Sprint.

# 17. Agile Framework Comparison

| Framework | Main Idea | Strength | Limitation | Suitability |
| --- | --- | --- | --- | --- |
| Scrum | Time-boxed Sprints with defined roles and ceremonies. | Clear structure, prioritization and regular feedback. | Requires discipline around Sprint events and roles. | High |
| Kanban | Continuous flow using visual work limits. | Flexible and simple workflow. | Less prescriptive for Sprint planning. | Medium |
| XP | Engineering practices such as pair programming and continuous testing. | Strong software quality focus. | Can require strong technical discipline. | High as a supporting practice |
| Lean | Remove waste and maximize value. | Focuses on efficiency and value. | Less specific project-management structure. | Medium |
| LeSS | Scale Scrum across multiple teams. | Extends Scrum principles to larger products. | More coordination is required. | Low for a small academic team |
| SAFe | Structured scaling for large organizations. | Detailed enterprise coordination. | Heavy for a small project. | Low |
| Scrum@Scale | Scale Scrum through connected Scrum teams. | Useful for larger multi-team environments. | More complex than needed here. | Low |

## 17.1 Recommended Framework

Scrum is the most suitable primary framework for this mini-project because the system contains multiple functional areas that can be developed incrementally. Three-to-four major Sprints can deliver useful functionality in stages, while Sprint Reviews provide opportunities to obtain feedback and adjust priorities. XP practices such as testing and continuous integration can be used as supporting engineering practices.

# 18. Project Timeline and Release Roadmap

| Period | Activity | Output |
| --- | --- | --- |
| Week 1 | Product discovery and backlog creation | Vision, requirements, personas, epics and stories |
| Week 2 | Sprint 1 | Authentication and project foundation |
| Week 3 | Sprint 2 | Student management |
| Week 4 | Sprint 3 | Course and attendance management |
| Week 5 | Sprint 4 | Marks and academic performance |
| Week 6 | Sprint 5 | Notifications, reports and dashboard enhancements |
| Final Phase | Integration, testing and documentation | Release-ready academic management platform |

## 18.1 Release Roadmap

Release 1: Foundation – secure access and basic platform structure.

Release 2: Student Records – complete student record workflow.

Release 3: Academic Operations – courses and attendance.

Release 4: Performance – marks, grades and results.

Release 5: Communication and Insights – notifications, reports and dashboard.

# 19. Complete Agile Documentation Checklist

1. Agile Project Planning Report – Included in this document.

2. Product Vision Document – Included in this document.

3. Scrum Team Structure – Included in this document.

4. Scrum Roles and Responsibilities – Included in this document.

5. Epic Documentation – Included in this document.

6. User Story Repository – Included in this document.

7. Acceptance Criteria Document – Included in this document.

8. Prioritized Product Backlog – Included in this document.

9. Story Point Estimation Sheet – Included in this document.

10. Sprint Planning Document – Included in this document.

11. Sprint Backlog – Included in this document.

12. Scrum Board – Included in this document.

13. Burndown Chart – Included in this document.

14. Sprint Review Report – Included in this document.

15. Sprint Retrospective Report – Included in this document.

16. Agile Framework Comparison Report – Included in this document.

17. Project Timeline and Release Roadmap – Included in this document.

18. Complete Agile Documentation – Included in this document.

## 19.1 Final Quality Check

All seven requested epics are represented.

User stories use a clear Agile format.

Acceptance criteria are measurable.

Backlog items are prioritized.

Story points follow the requested scale.

Sprint goals and Sprint Backlogs are defined.

Scrum Board workflow is documented.

Burndown tracking is included.

All four core Scrum ceremonies are explained.

Agile frameworks are compared and Scrum is recommended.

Timeline and release roadmap are included.

# 20. Conclusion

The Student Record and Academic Management Platform can be developed effectively using Scrum because its requirements naturally divide into independent but connected capabilities. Starting with authentication and project setup creates a foundation, followed by student management, course and attendance functions, and then marks, reporting and enhancements.

The Agile approach keeps the Product Backlog visible, gives priority to high-value functionality, estimates work using story points, and delivers working increments through Sprints. Sprint Reviews provide stakeholder feedback, while Retrospectives help the team improve its process. This makes the project easier to manage, test and adapt than attempting to build the complete platform in one large development cycle.

Overall, the documentation provides a structured Agile plan from product discovery through release planning and includes the major deliverables required for the Unit-2 mini-project.